## in
APR Reporting Year | Action ref | SSSI name | Area of SSSI unit in WW ownership | Action type | Action completed
2020-2021 | 3.1 | Box Mine | 0.88 | Land Management Review | Review land management, to include management sustainability, the current management plan and any operational constraints. Produce and agree updated management plan.
2020-2021 | 3.2 | Box Mine | 0.88 | Remedies Delivery | Deliver remedies and actions, namely to enhance the setting of the adjacent bat roost through amended grassland management and hedgerow planting.
2020-2021 | 5.1 | Isle of Portland | 0.12 | Land Management Review | Review land management, to include management sustainability and any operational constraints. Produce and agree a management plan.
2020-2021 | 5.2 | Isle of Portland | 0.12 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review, namely: periodically review scrub establishment and remove any non-native species.
2020-2021 | 22.1 | River Avon System | 0.05 | Land Management Review | Review land management, to include management sustainability and any operational constraints: Produce and agree a management plan
2020-2021 | 22.2 | River Avon System | 0.05 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review. Deliver capital works and implement management plan, including: fell Cypress tree line (along boundary) that shade and potentially dry out the adjacent SSSI; and leave stumps in situ and manage habitat as tall ruderal/early successional scrub.
2020-2021 | 36.1 | South Exmoor | 3.01 | Land Management Review | Review land management, to include management sustainability, the current management plan and any operational constraints. Produce and agree updated management plan.
2020-2021 | 36.2 | South Exmoor | 3.01 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review, including removal and treatment of all rhododendron
2020-2021 | 40.1 | Trill Quarry | 1.4 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2020-2021 | 40.2 | Trill Quarry | 1.4 | Land Management Review | Review land management, to include management sustainability and any operational constraints: Produce and agree an updated management plan
2020-2021 | 41.1 | Upton Heath | 2.76 | Land Management Review | Review, clarify and agree new tenancy to ensure sustainable ongoing management
2020-2021 | 41.2 | Upton Heath | 2.76 | Remedies Delivery | Deliver remedies and actions, as identified with Natural England and the tenant, including: remove and treat/kill all trees (including saplings) that are located outside of two ‘tree retention areas’ (total retained area approx. 10% of the unit, hence meeting the Favourable Condition Table), retaining six scattered, mature ‘landscape feature’ maritime pines outside of the tree retention area in agreement with the tenant. In addition, removal of any juvenile maritime pine which is within the tree retention areas; remove areas of thick tall gorse/bramble/saplings mechanically and burn (following the tenant's standard specification). These areas will then be maintained through increased grazing pressure; install a ‘Clipex’ fence along the western boundary to replace the defunct fence line following the scrub clearance, maintaining the boundary for grazing animals and also allowing suitable conservation grazing on adjacent land to the west (which is owned by the tenant).
2020-2021 | 42.1 | Upton Heath | 0.14 | Remedies Delivery | Section of site an access route, management of habitat adjacent to the track delivered by the tenant for action 41.2. See agreed actions relating to Action 41.2, namely: remove and treat/kill all trees (including saplings) that are located outside of two ‘tree retention areas’ (total retained area approx. 10% of the unit, hence meeting the Favourable Condition Table). The retention areas were agreed in conjunction with the tenant and utilising their knowledge of the wider SSSI; remove areas of thick tall gorse/bramble/saplings mechanically and burn (following the tenant's standard specification). These areas will then be maintained through increased grazing pressure.
2020-2021 | 43.1 | Upton Heath | 1.19 | Land Management Review | Review land management, to include management sustainability, management plan review and identify any appropriate capital works (with input from NE), including: Update management plan.
2020-2021 | 43.2 | Upton Heath | 1.19 | Remedies Delivery | Implement management plan, including: clear site of trees and saplings, treating and removing regrowth; remove non-native species; manage gorse to create a mosaic of varying age and structure; clear encroaching bramble; and create a mosaic of bare ground for reptiles.
2020-2021 | 44.1 | White Horse Hill | 18.36 | Land Management Review | Review and agree new tenancy to ensure sustainable ongoing management
2020-2021 | 44.2 | White Horse Hill | 18.36 | Land Management Review | Review land management, to include management sustainability, management plan review and identify any appropriate capital works. Facilitate implementation of an agri-environment scheme, to include: establish mixed grazing - adequate stocking of sheep (July – February), cattle (March to October) and / or horses (all year); scrub control - adequate reduction and thereafter control of scrub growth (primarily gorse); and burning – possibly patch burning to reduce tor grass biomass.
2020-2021 | 45.1 | White Horse Hill | 2.09 | Land Management Review | Review land management, to include management sustainability, management plan review and identify any appropriate capital works: produce updated management plan.
2020-2021 | 45.2 | White Horse Hill | 2.09 | Remedies Delivery | Implement management plan, including: Grassland: removal of pampass grass; Grassland: one-off initial scarification of the grassland to create up to 30% bare ground to reduce thatch and create opportunities for establishment of herb species; Grassland: two cut-and-collects to be undertaken each year (outside operational areas) to reduce dominance of rough grasses; Woodland: maintain an access path to enable contractors (volunteers) to access the site; Woodland: continue rotational hazel coppicing; and Woodland: maintain woodland boundaries to deter unauthorised access.
2020-2021 | 46.1 | White Horse Hill | 0.53 | Land Management Review | Revise tenancy and bring management of the land parcel back under Wessex Water control.
2021-2022 | 6.1 | Monkswood Valley | 4.69 | Condition Review | Undertake a condition review to identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 7.1 | Monkswood Valley | 0.57 | Condition Review | Undertake a condition review to identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 8.1 | Monkswood Valley | 4.9 | Condition Review | Undertake a condition review to identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 9.1 | North Exmoor | 6.19 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 10.1 | Poole Harbour | 0.37 | Land Management Review | Review land management, to include management sustainability and any operational constraints. Produce management plan.
2021-2022 | 16.1 | Quants | 0.32 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 17.1 | Quants | 5.44 | Condition Review | Undertake a condition review to identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 17.2 | Quants | 5.44 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 18.1 | Quants | 14.32 | Condition Review | Undertake a condition review to identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 18.2 | Quants | 14.32 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 19.1 | Quants | 0.42 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 20.1 | Quants | 0.15 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 21.1 | Quants | 0.2 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 25.1 | Severn Estuary | 4.63 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment and updated botanical survey of the saltmarsh habitats, in part to ensure that sea couch is not becoming dominant.
2021-2022 | 26.1 | Shapwick Heath | 42.38 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 27.1 | Shapwick Heath | 1.98 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 28.1 | Shapwick Heath | 0.42 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 29.1 | Shapwick Heath | 48.4 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 30.1 | Shapwick Heath | 4.18 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 31.1 | Shapwick Heath | 2.27 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 32.1 | Shapwick Heath | 1.03 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 33.1 | Shapwick Heath | 0.34 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 34.1 | Shapwick Heath | 0.89 | Land Management Review | Ensure the tenant has a current management plan
2021-2022 | 37.1 | St. Catherine's Valley | 19.17 | Condition Review | Undertake a condition review to inform an agri-environment scheme application and enable suitable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 38.1 | St. Catherine's Valley | 21.98 | Condition Review | Undertake a condition review to inform an agri-environment scheme application and enable suitable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 39.1 | St. Catherine's Valley | 3.15 | Condition Review | Undertake a condition review to inform an agri-environment scheme application and enable suitable monitoring of change: Complete appropriate Condition Assessment.
2021-2022 | 40.3 | Trill Quarry | 1.4 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review. Deliver capital works and implement management plan, including: removal of trees overhanging the geological exposure; periodic clearance of vegetation, litter and brash that may be covering the exposure; and agree access 'in principle' to enable specialist groups to visit the geological feature.
2022-2023 | 1.1 | Black Hill Heath | 0.46 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2022-2023 | 2.1 | Black Hill Heath | 0.4 | Condition Review | Undertake a condition review to inform an agri-environment scheme application and enable suitable monitoring of change: Complete appropriate Condition Assessment.
2022-2023 | 6.2 | Monkswood Valley | 4.69 | Land Management Review | Review land management, to include management sustainability and any operational constraints. Produce a woodland management plan. It is noted that the management plan should also include measures for managing ash dieback.
2022-2023 | 7.2 | Monkswood Valley | 0.57 | Land Management Review | Review land management, to include management sustainability and any operational constraints. Produce a woodland management plan. It is noted that the management plan should also include measures for managing ash dieback.
2022-2023 | 8.2 | Monkswood Valley | 4.9 | Land Management Review | Review land management, to include management sustainability and any operational constraints. Produce a woodland management plan. It is noted that the management plan should also include measures for managing ash dieback.
2022-2023 | 9.2 | North Exmoor | 6.19 | Land Management Review | Review land management, to include management sustainability, the current management plan and any operational constraints: Produce and agree updated management plan
2022-2023 | 11.1 | Prior's Park & Adcombe Wood | 36.6 | Condition Review | Undertake a condition review to identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2022-2023 | 11.2 | Prior's Park & Adcombe Wood | 36.6 | Land Management Review | Ensure the tenant has a current management plan
2022-2023 | 13.1 | Purbeck Ridge (East) | 11.51 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2022-2023 | 14.1 | Purbeck Ridge (East) | 0.29 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2022-2023 | 15.1 | Purbeck Ridge (East) | 0.89 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2022-2023 | 35.1 | South Dorset Coast | 0.21 | Condition Review | Undertake a condition review to fully identify appropriate management and enable monitoring of change: Complete appropriate Condition Assessment.
2022-2023 | 46.2 | White Horse Hill | 0.53 | Land Management Review | Review land management, to include management sustainability, management plan review and identify any appropriate capital works: produce updated management plan.
2023-2024 | 1.2 | Black Hill Heath | 0.46 | Land Management Review | Review land management, to include management sustainability, the current management plan and any operational constraints: Produce and agree updated management plan
2023-2024 | 2.2 | Black Hill Heath | 0.4 | Land Management Review | Review and agree new tenancy to ensure sustainable ongoing management
2023-2024 | 4.1 | Canford Heath | 0.37 | Land Management Review | Review land management, to include management sustainability, the current management plan and any operational constraints. Produce and agree updated management plan.
2023-2024 | 9.3 | North Exmoor | 6.19 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review. Deliver capital works and implement management plan, including: I. treatment of tree regeneration and scrub; II. introduction of rotational cutting to diversify age structure of heather canopy/promote young bilberry shoots for common cow-wheat; III. bracken management; IV. control of non-native, invasive species; V. monitoring of gorse on northern bank of the site to ensure that rowan or other trees are not encroaching/the bank is not succeeding to secondary woodland.
2023-2024 | 10.2 | Poole Harbour | 0.37 | Land Management Review | Wessex Water currently has no established access to the SSSI section of the site. Review and implement suitable access.
2023-2024 | 14.2 | Purbeck Ridge (East) | 0.29 | Land Management Review | Review land management, to include management sustainability, the current management plan and any operational constraints: Produce and agree updated management plan
2023-2024 | 15.2 | Purbeck Ridge (East) | 0.89 | Land Management Review | Review land management, to include management sustainability, the current management plan and any operational constraints: Produce and agree updated management plan
2023-2024 | 15.3 | Purbeck Ridge (East) | 0.89 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review. Deliver capital works and implement management plan, including: - scrub control: peridoically cut back boundary hedgerows and trees to reduce encroachment and shade on grassland; - Grassland management: cut and remove arisings ordinarily twice per year; once between early July to October and once between mid-February and mid-March, with provision for a third cut in September or October (if necessary given volume of grass growth and if weather conditions allow) in exceptional years where the seasonal conditions dictate that an early summer cut (July up to mid-August) is necessary
2023-2024 | 24.1 | Ruttersleigh | 13.82 | Condition Review | Undertake a condition review to inform an agri-environment scheme application and enable suitable monitoring of change: Complete appropriate Condition Assessment.
2023-2024 | 25.2 | Severn Estuary | 4.63 | Land Management Review | Review land management, to include management sustainability, the current management plan and any operational constraints: produce updated management plan, considering: - management of the disturbance to roosting waders, notably redshank, on the banks of the River Axe; - grazing of the saltmarsh habitat.
2023-2024 | 35.2 | South Dorset Coast | 0.21 | Land Management Review | Review land management, to include management sustainability and any operational constraints: Produce and agree a management plan
2023-2024 | 35.3 | South Dorset Coast | 0.21 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review. Deliver capital works and implement management plan, including: - amend grassland management; - clear and treat scrub and manage area on a rotation; - push back hedgerow encroachment and manage area on a rotation; - Control all growing Himalayan balsam.
2023-2024 | 38.2 | St. Catherine's Valley | 21.98 | Land Management Review | Facilitate implementation of an appropriate agri-environment scheme
2023-2024 | 46.3 | White Horse Hill | 0.53 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review. Deliver capital works and implement management plan, including: - maintain an access path to enable contractors (volunteers) to access the site; - manage bramble encroachment; - take annual cut-and-collect of the dry grassland; - manage reed bed area through rotational management; - maintain boundaries to deter unauthorised access.
2024-2025 | 1.3 | Black Hill Heath | 0.46 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review. Deliver capital works and implement management plan, including: - treatment of trees and scrub; - removal of buddleia; - diversification of gorse cover and structure; - bracken management; - creation of bare substrate for invertebrates; - grassland management on reservoir top.
2024-2025 | 2.3 | Black Hill Heath | 0.4 | Land Management Review | Facilitate implementation of an agri-environment scheme to include: - reduction in tree and shrub cover to meet Favourable Condition Table standards; - removal and treatment of pine regeneration; - bracken and gorse management.
2024-2025 | 4.2 | Canford Heath | 0.37 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review, including: - treatment of trees and scrub; - removal of buddleia and bay laurel; - ragwort control; - diversification of gorse and heather cover and structure; and - bracken management.
2024-2025 | 6.3 | Monkswood Valley | 4.69 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review, to include: - ash dieback mitigation; - introduction of small scale hazel coppicing; - creation of areas of open canopy (clearings, glades and rides); - removal of pheasant pens; - removal of fly-tipping; - fix fences.
2024-2025 | 7.3 | Monkswood Valley | 0.57 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review, to include: - ash dieback mitigation; - introduction of small scale hazel coppicing; - creation of areas of open canopy (clearings, glades and rides); - removal of pheasant pens; - removal of fly-tipping; - fix fences.
2024-2025 | 8.3 | Monkswood Valley | 4.9 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review, to include: - ash dieback mitigation; - introduction of small scale hazel coppicing; - creation of areas of open canopy (clearings, glades and rides); - removal of pheasant pens; - removal of fly-tipping; - fix fences.
2024-2025 | 10.3 | Poole Harbour | 0.37 | Remedies Delivery | Deliver remedies and actions, as identified by the land management plan, including the removal of fly tipping.
2024-2025 | 13.2 | Purbeck Ridge (East) | 11.51 | Land Management Review | Facilitate implementation of an agri-environment scheme, to include grazing amendments (graze with cattle in summer, sheep in winter) or cut for hay in summer.
2024-2025 | 14.3 | Purbeck Ridge (East) | 0.29 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review. Deliver capital works and implement management plan, including: - scrub control: removal of scrub around covered reservoir; - grassland management: varied patchwork cut and remove in late-summer most years.
2024-2025 | 19.2 | Quants | 0.42 | Land Management Review | Review tenure of the land: lease land to Forestry England, who currently have lease of the wider SSSI unit from Wessex Water, to allow consistent and holistic management of the entire SSSI unit.
2024-2025 | 19.3 | Quants | 0.42 | Land Management Review | Ensure the tenant has a current management plan
2024-2025 | 24.2 | Ruttersleigh | 13.82 | Land Management Review | Review and agree new tenancy to ensure sustainable ongoing management
2024-2025 | 24.3 | Ruttersleigh | 13.82 | Land Management Review | Ensure the occupier has a current management plan
2024-2025 | 25.3 | Severn Estuary | 4.63 | Remedies Delivery | Deliver remedies and actions, as identified by the land management review.
2024-2025 | 37.2 | St. Catherine's Valley | 19.17 | Land Management Review | Review potential for agri-environment scheme application. If an agri-environment scheme application is not feasible, work with the tenant to develop a management plan to be delivered outside of the scope of agri-environment schemes.
2024-2025 | 39.2 | St. Catherine's Valley | 3.15 | Land Management Review | Facilitate implementation of an appropriate agri-environment scheme.